## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | 后端工作 | 13 days? | 2018 October 15 8:00 | 2018 October 31 17:00 |  | 1
2 | Yes | Auto Scheduled | 后台管理网站 | 6 days | 2018 October 15 8:00 | 2018 October 22 17:00 |  | 2
3 | Yes | Auto Scheduled | 网站功能 | 6 days | 2018 October 15 8:00 | 2018 October 22 17:00 |  | 3
4 | Yes | Auto Scheduled | 发卡功能 | 2 days | 2018 October 15 8:00 | 2018 October 16 17:00 |  | 4
5 | Yes | Auto Scheduled | 区域权限设置 | 2 days | 2018 October 17 8:00 | 2018 October 18 17:00 |  | 4
6 | Yes | Auto Scheduled | 网页调用3D软件 | 2 days | 2018 October 19 8:00 | 2018 October 22 17:00 |  | 4
7 | Yes | Auto Scheduled | 网站优化 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 3
8 | Yes | Auto Scheduled | 页面按需更新 | 2 days | 2018 October 15 8:00 | 2018 October 16 17:00 |  | 4
9 | Yes | Auto Scheduled | Web定位展示 | 2 days | 2018 October 18 8:00 | 2018 October 19 17:00 |  | 4
10 | Yes | Auto Scheduled | 对接3D顶视图接口 | 2 days | 2018 October 18 8:00 | 2018 October 19 17:00 |  | 5
11 | Yes | Auto Scheduled | 定位后台处理 | 12 days? | 2018 October 15 8:00 | 2018 October 30 17:00 |  | 2
12 | Yes | Auto Scheduled | 定位引擎配置工具 | 4 days? | 2018 October 15 8:00 | 2018 October 18 17:00 |  | 3 | 根据品铂数据库生成基站和定位信息
13 | Yes | Auto Scheduled | 读写数据库数据 | 2 days? | 2018 October 15 8:00 | 2018 October 16 17:00 |  | 4
14 | Yes | Auto Scheduled | 基站信息 | 1 day? | 2018 October 15 8:00 | 2018 October 15 17:00 |  | 5
15 | Yes | Auto Scheduled | 定位卡信息 | 1 day? | 2018 October 16 8:00 | 2018 October 16 17:00 |  | 5
16 | Yes | Auto Scheduled | 基站设置功能集成 | 3 days? | 2018 October 16 8:00 | 2018 October 18 17:00 |  | 4
17 | Yes | Auto Scheduled | 后端实现 | 1 day? | 2018 October 16 8:00 | 2018 October 16 17:00 |  | 5
18 | Yes | Auto Scheduled | 前端(web)调用 | 1 day? | 2018 October 18 8:00 | 2018 October 18 17:00 |  | 5
19 | Yes | Auto Scheduled | 前端(3d)调用 | 1 day? | 2018 October 17 8:00 | 2018 October 17 17:00 |  | 5
20 | Yes | Auto Scheduled | 设置功能 | 4 days | 2018 October 17 8:00 | 2018 October 22 17:00 |  | 3
21 | Yes | Auto Scheduled | 发卡功能 | 3 days | 2018 October 17 8:00 | 2018 October 19 17:00 |  | 4
22 | Yes | Auto Scheduled | 区域权限设置 | 2 days | 2018 October 19 8:00 | 2018 October 22 17:00 |  | 4
23 | Yes | Auto Scheduled | 定位数据优化 | 6 days | 2018 October 23 8:00 | 2018 October 30 17:00 |  | 3
24 | Yes | Auto Scheduled | "无用点"过滤 | 3 days | 2018 October 23 8:00 | 2018 October 25 17:00 |  | 4
25 | Yes | Auto Scheduled | "关键点"提取 | 3 days | 2018 October 26 8:00 | 2018 October 30 17:00 |  | 4
26 | Yes | Auto Scheduled | 数据对接 | 13 days? | 2018 October 15 8:00 | 2018 October 31 17:00 |  | 2
27 | Yes | Auto Scheduled | 对外接口 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 3 | RestFul
28 | Yes | Auto Scheduled | 基本信息对外接口 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4 | 资源对象增删改查
29 | Yes | Auto Scheduled | 操作功能对外接口 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4 | 发卡、配置权限
30 | Yes | Auto Scheduled | 定位顶视图接口 | 2 days | 2018 October 15 8:00 | 2018 October 16 17:00 |  | 4 | 需要3D发送数据
31 | Yes | Auto Scheduled | 对接模拟 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 3
32 | Yes | Auto Scheduled | 拉取信息 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4
33 | Yes | Auto Scheduled | 对接数据 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
34 | Yes | Auto Scheduled | SIS设备数据 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 6
35 | Yes | Auto Scheduled | 门禁数据记录 | 1 day | 2018 October 15 8:00 | 2018 October 15 17:00 |  | 6
36 | Yes | Auto Scheduled | 摄像头数据 | 1 day | 2018 October 15 8:00 | 2018 October 15 17:00 |  | 6
37 | Yes | Auto Scheduled | 同步数据 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
38 | Yes | Auto Scheduled | 人员&组织架构 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 6
39 | Yes | Auto Scheduled | 区域&设备 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 6
40 | Yes | Auto Scheduled | 被拉取信息 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4
41 | Yes | Auto Scheduled | 实时位置数据 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
42 | Yes | Auto Scheduled | 历史位置数据 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
43 | Yes | Auto Scheduled | 基站信息（列表、详情） | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
44 | Yes | Auto Scheduled | 标签信息（列表、详情） | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
45 | Yes | Auto Scheduled | 同步数据信息 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
46 | Yes | Auto Scheduled | 被操作信息 | 1 day | 2018 October 15 8:00 | 2018 October 15 17:00 |  | 4
47 | Yes | Auto Scheduled | 基本信息对外接口 | 1 day | 2018 October 15 8:00 | 2018 October 15 17:00 |  | 5
48 | Yes | Auto Scheduled | 设置功能对外接口 | 1 day | 2018 October 15 8:00 | 2018 October 15 17:00 |  | 5
49 | Yes | Auto Scheduled | 对接联调 | 13 days? | 2018 October 15 8:00 | 2018 October 31 17:00 |  | 3
50 | Yes | Auto Scheduled | 推送信息 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4
51 | Yes | Auto Scheduled | 消息队列接口 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
52 | Yes | Auto Scheduled | 告警推送 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
53 | Yes | Auto Scheduled | 门禁状态推送 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
54 | Yes | Auto Scheduled | 拉取信息 | 10 days | 2018 October 15 8:00 | 2018 October 26 17:00 |  | 4
55 | Yes | Auto Scheduled | 同步数据 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
56 | Yes | Auto Scheduled | 人员&组织架构 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 6
57 | Yes | Auto Scheduled | 区域&设备 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 6
58 | Yes | Auto Scheduled | 对接数据 | 10 days | 2018 October 15 8:00 | 2018 October 26 17:00 |  | 5
59 | Yes | Auto Scheduled | 两票数据 | 5 days | 2018 October 22 8:00 | 2018 October 26 17:00 |  | 6
60 | Yes | Auto Scheduled | 巡检数据 | 5 days | 2018 October 22 8:00 | 2018 October 26 17:00 |  | 6
61 | Yes | Auto Scheduled | SIS设备数据 | 5 days | 2018 October 22 8:00 | 2018 October 26 17:00 |  | 6
62 | Yes | Auto Scheduled | 设备告警列表 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 6
63 | Yes | Auto Scheduled | 门禁数据记录 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 6
64 | Yes | Auto Scheduled | 摄像头数据 | 5 days | 2018 October 22 8:00 | 2018 October 26 17:00 |  | 6
65 | Yes | Auto Scheduled | 被拉取信息 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4
66 | Yes | Auto Scheduled | 实时位置数据 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
67 | Yes | Auto Scheduled | 历史位置数据 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
68 | Yes | Auto Scheduled | 基站信息（列表、详情） | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
69 | Yes | Auto Scheduled | 标签信息（列表、详情） | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
70 | Yes | Auto Scheduled | 同步数据信息 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
71 | Yes | Auto Scheduled | 被操作信息 | 5 days? | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4
72 | Yes | Auto Scheduled | 基本信息对外接口 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 5
73 | Yes | Auto Scheduled | 设置功能对外接口 | 1 day? | 2018 October 15 8:00 | 2018 October 15 17:00 |  | 5
74 | Yes | Auto Scheduled | 定位实时数据联调 | 8 days | 2018 October 22 8:00 | 2018 October 31 17:00 |  | 4
75 | Yes | Auto Scheduled | 基站设置 | 3 days | 2018 October 22 8:00 | 2018 October 24 17:00 |  | 5
76 | Yes | Auto Scheduled | 数据录入 | 3 days | 2018 October 22 8:00 | 2018 October 24 17:00 |  | 5
77 | Yes | Auto Scheduled | 定位联调 | 5 days | 2018 October 25 8:00 | 2018 October 31 17:00 |  | 5
78 | Yes | Auto Scheduled | 打包部署 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 2
79 | Yes | Auto Scheduled | 前端(3D)工作 | 20 days | 2018 October 15 8:00 | 2018 November 9 17:00 |  | 1
80 | Yes | Auto Scheduled | 模型展示 | 10 days | 2018 October 15 8:00 | 2018 October 26 17:00 |  | 2
81 | Yes | Auto Scheduled | 建模 | 10 days | 2018 October 15 8:00 | 2018 October 26 17:00 |  | 3
82 | Yes | Auto Scheduled | 主厂房管道 | 2 days | 2018 October 15 8:00 | 2018 October 16 17:00 |  | 4
83 | Yes | Auto Scheduled | 生产设备可动部件动画 | 5 days | 2018 October 22 8:00 | 2018 October 26 17:00 |  | 4 | 发电机、燃气机 运作效果动画
84 | Yes | Auto Scheduled | 模型调整 | 10 days | 2018 October 15 8:00 | 2018 October 26 17:00 |  | 4 | 尺寸、配色
85 | Yes | Auto Scheduled | 地形中的机房分离出来 | 5 days | 2018 October 22 8:00 | 2018 October 26 17:00 |  | 4
86 | Yes | Auto Scheduled | 生产设备 | 5 days | 2018 October 22 8:00 | 2018 October 26 17:00 |  | 4 | 用户联调SIS数据用的有代表性的几个设备
87 | Yes | Auto Scheduled | 加入模型 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 3
88 | Yes | Auto Scheduled | 主厂房内设备展示 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4
89 | Yes | Auto Scheduled | 其他次要设备 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4
90 | Yes | Auto Scheduled | 建筑模型分层处理(增量) | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4
91 | Yes | Auto Scheduled | 定位优化 | 15 days | 2018 October 15 8:00 | 2018 November 2 17:00 |  | 2
92 | Yes | Auto Scheduled | 大量人员数据测试以及优化 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 3
93 | Yes | Auto Scheduled | 前端展示大量人员 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4 | （需要优化）
94 | Yes | Auto Scheduled | 历史数据大数据量测试 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4 | 查询速度测试并优化
95 | Yes | Auto Scheduled | 多人轨迹测试并优化 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4
96 | Yes | Auto Scheduled | 定位展示效果优化 | 15 days | 2018 October 15 8:00 | 2018 November 2 17:00 |  | 3
97 | Yes | Auto Scheduled | 人员状态效果展示 | 3 days | 2018 October 15 8:00 | 2018 October 17 17:00 |  | 4 | 在线，休眠，离线。在线（在有效区域活动）、休眠（在有效区域停止）、离线（离开有效区域）
98 | Yes | Auto Scheduled | 男女人物模型 | 2 days | 2018 October 15 8:00 | 2018 October 16 17:00 |  | 4
99 | Yes | Auto Scheduled | 轨迹效果优化 | 8 days | 2018 October 15 8:00 | 2018 October 24 17:00 |  | 4
100 | Yes | Auto Scheduled | 进出有效区域 | 3 days | 2018 October 15 8:00 | 2018 October 17 17:00 |  | 5
101 | Yes | Auto Scheduled | 楼层间轨迹 | 3 days | 2018 October 17 8:00 | 2018 October 19 17:00 |  | 5
102 | Yes | Auto Scheduled | 进出建筑轨迹 | 3 days | 2018 October 22 8:00 | 2018 October 24 17:00 |  | 5
103 | Yes | Auto Scheduled | 区域效果优化 | 1 day | 2018 October 22 8:00 | 2018 October 22 17:00 |  | 4
104 | Yes | Auto Scheduled | 位置穿墙问题处理 | 5 days | 2018 October 29 8:00 | 2018 November 2 17:00 |  | 4
105 | Yes | Auto Scheduled | 实时人员拓扑树 | 3 days | 2018 October 15 8:00 | 2018 October 17 17:00 |  | 3
106 | Yes | Auto Scheduled | 设备 | 10 days | 2018 October 15 8:00 | 2018 October 26 17:00 |  | 2
107 | Yes | Auto Scheduled | 设备数据录入 | 10 days | 2018 October 15 8:00 | 2018 October 26 17:00 |  | 3
108 | Yes | Auto Scheduled | 门禁设备 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4
109 | Yes | Auto Scheduled | 摄像头设备 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 4
110 | Yes | Auto Scheduled | 消防 | 5 days | 2018 October 22 8:00 | 2018 October 26 17:00 |  | 4
111 | Yes | Auto Scheduled | 周界报警 | 5 days | 2018 October 22 8:00 | 2018 October 26 17:00 |  | 4
112 | Yes | Auto Scheduled | 装饰品设备 | 5 days | 2018 October 22 8:00 | 2018 October 26 17:00 |  | 4
113 | Yes | Auto Scheduled | KKS设备信息录入 | 3 days | 2018 October 15 8:00 | 2018 October 17 17:00 |  | 4 | 并摆放在3D位置中
114 | Yes | Auto Scheduled | 大设备独立展示 | 3 days | 2018 October 22 8:00 | 2018 October 24 17:00 |  | 3
115 | Yes | Auto Scheduled | 大数据量设备展示优化 | 5 days | 2018 October 15 8:00 | 2018 October 19 17:00 |  | 3
116 | Yes | Auto Scheduled | 对接展示 | 10 days | 2018 October 29 8:00 | 2018 November 9 17:00 |  | 2
117 | Yes | Auto Scheduled | 动环设备 | 6 days | 2018 October 29 8:00 | 2018 November 5 17:00 |  | 3
118 | Yes | Auto Scheduled | 设备告警 | 2 days | 2018 October 29 8:00 | 2018 October 30 17:00 |  | 4
119 | Yes | Auto Scheduled | 设备区域报警 | 2 days | 2018 October 31 8:00 | 2018 November 1 17:00 |  | 4 | 消防、周界
120 | Yes | Auto Scheduled | 摄像头 | 4 days | 2018 October 31 8:00 | 2018 November 5 17:00 |  | 4 | 视频
121 | Yes | Auto Scheduled | SIS设备 | 3 days | 2018 October 29 8:00 | 2018 October 31 17:00 |  | 3
122 | Yes | Auto Scheduled | 两票展示功能 | 10 days | 2018 October 29 8:00 | 2018 November 9 17:00 |  | 3 | 工作票、操作票的内容可能不同
123 | Yes | Auto Scheduled | 巡检展示功能 | 10 days | 2018 October 29 8:00 | 2018 November 9 17:00 |  | 3
124 | Yes | Auto Scheduled | 其他 | 18 days | 2018 October 15 8:00 | 2018 November 7 17:00 |  | 2
125 | Yes | Auto Scheduled | 漫游 | 18 days | 2018 October 15 8:00 | 2018 November 7 17:00 |  | 3
126 | Yes | Auto Scheduled | 室内漫游 | 3 days | 2018 October 15 8:00 | 2018 October 17 17:00 |  | 4
127 | Yes | Auto Scheduled | 人物走动动画切换 | 3 days | 2018 November 5 8:00 | 2018 November 7 17:00 |  | 4

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 |  | zyy | Work |  | 建模 |  |  | 100% | ¥0.00/h | 0
2 |  | lzx | Work |  | 建模 |  |  | 100% | ¥0.00/h | 0
3 |  | yzl | Work |  | 3D开发 |  |  | 100% | ¥0.00/h | 0
4 |  | wk | Work |  | 3D开发 |  |  | 100% | ¥0.00/h | 0
5 | 蔡万伟 | cww | Work |  |  |  |  | 100% | ¥0.00/h | 0
6 |  | ljf | Work |  | 后台 |  |  | 100% | ¥0.00/h | 0
7 |  | ljp | Work |  | UI |  |  | 100% | ¥0.00/h | 0
8 |  | cxl | Work |  | 3D开发 |  |  | 100% | ¥0.00/h | 0
9 |  | wcw | Work |  | 3D开发后备 |  |  | 100% | ¥0.00/h | 0
10 | BS前端 | B | Work |  |  |  |  | 100% | ¥0.00/h | 0
11 |  |  | Work |  |  |  |  | 100% | ¥0.00/h | 0
12 |  |  | Work |  |  |  |  | 100% | ¥0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units